Debe ser un valor entero mayor de 0
El valor debe ser una fecha
Duración mínima 3, máxima 24 (días laborables)
## Config
Proyect
Name of the project

Sprint Number	Start date	Days	Working days
1	3-abr-14	11	11

TASKS		TEAM	BANK HOLIDAYS
TYPES	STATUS
Analysis	Pending
Design	In progress
Code	Finished
Test	Removed

## Data
		SPRINT	START	DURATION
		1	3-abr-14	11			J	V	L	M	X	J	V	L	M	X	J	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?
							3-abr	4-abr	7-abr	8-abr	9-abr	10-abr	11-abr	14-abr	15-abr	16-abr	17-abr	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?
				Remaining Tasks				4	3	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0					Analysis	Pending	0
				Remaining working hours			13,5	9	7	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0					Design	In progress	0
SPRINT BACKLOG							EFFORT					Code	Finished	0
Backlog ID	Task			Type	Status	Responsible					Test	Removed	0
Follow some tutorials, see Angular videos in combination with other technologies	Get clear Angular philosophy			Analysis	Finished		2	0	0					0	0	0
See advantages of Heroku, decide if it is worth as my deployment site. Decide what to do with my mySQL database, if migrate to Postgre or not	Do some research on deployment sites			Analysis	Finished		2,5	0	0					0	0	0
New API function get timeseries. Install dygraphs. Use that data from server to represent a simple timeseries	First static graph with dygraph			Code	Pending		2	2	0					0	0	0
As my scope is to get a dinamic dashboard, I could start giving the functionality. This very basic feature would display a menu and let me choose from an option, which is to create the graph	Make a menu that allows me to build that graph			Code	Pending		2	2	2					0	0	0
Use some CSS, investigate on how I could do it	Transform application into a visually attractive one			Code	Pending		3	3	3					0	0	0
Investigate on how I could do it. Gridster. JqueryWii, use a grid sistem somehow	Allow graphs to resize and move on dashboard			Code	Pending		2	2	2					0	0	0
									0	0	0
									0	0	0
									0	0	0

									0	0

## Graphs
	Project					SPRINT		START		DAYS
	Name of the project					1		3-abr-14		11

Effot Graphic / Remaining working hours

Tasks Graphic / Remaining Taks

Members Graphic / Remaining Working Hours

	3-abr	4-abr	7-abr	8-abr	9-abr	10-abr	11-abr	14-abr	15-abr	16-abr	17-abr	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0