Debe ser un valor entero mayor de 0
El valor debe ser una fecha
Duración mínima 3, máxima 24 (días laborables)
## Config
				User stories

Proyect					1. Visualize a decent webpage on client side, not only text
Name of the project					2. Show up some graph related to the project

Sprint Number	Start date	Days	Working days
2	28-mar-14	4	4

TASKS		TEAM	BANK HOLIDAYS
TYPES	STATUS
Analysis	Pending
Design	In progress
Code	Finished
Test	Removed

## Data
		SPRINT	START	DURATION
		2	28-mar-14	4			V	S	D	L	M	X	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?
							28-mar	29-mar	30-mar	31-mar	1-abr	2-abr	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?
				Remaining Tasks				6	5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0					Analysis	Pending	0
				Remaining working hours			8	6	5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0					Design	In progress	0
SPRINT BACKLOG							EFFORT					Code	Finished	0
	Task			Type	Status	Responsible					Test	Removed	0
1	Investigate on Angular			Analysis	Pending		2	1	0					0	0	0
1	Install Angular on server			Design	Pending		0,5	0,5	0,5					0	0	0
1	Build a decent html with angular			Code	Pending		1,5	1,5	1,5					0	0	0
1	Show up JSON ncommits with Angular			Code	Pending		0,5	0,5	0,5					0	0	0
2	Investigate on Dygraphs			Analysis	Pending		1	0	0					0	0	0
	Send JSON timeseries to browser			Code	Pending		0,5	0,5	0,5					0	0	0
	Represent that timeseries on a graph			Code	Pending		2	2	2					0	0	0
									0	0	0
									0	0	0

									0	0

## Graphs
	Project					SPRINT		START		DAYS
	Name of the project					2		28-mar-14		4

Effot Graphic / Remaining working hours

Tasks Graphic / Remaining Taks

Members Graphic / Remaining Working Hours

	28-mar	29-mar	30-mar	31-mar	1-abr	2-abr	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0