Debe ser un valor entero mayor de 0
El valor debe ser una fecha
Duración mínima 3, máxima 24 (días laborables)
## Config
Proyect
Custom software projects dashboard

Sprint Number	Start date	Days	Working days
1	25-mar-14	4	4

TASKS		TEAM	BANK HOLIDAYS
TYPES	STATUS
Analysis	Pending	Student1
Design	In progress	Student2
Code	Finished	Student3
Test	Removed	Student4

## Data
		SPRINT	START	DURATION
		1	25-mar-14	4			M	X	J	V	L	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?
							25-mar	26-mar	27-mar	28-mar	31-mar	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?
				Remaining Tasks				7	3	1	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0					Analysis	Pending	Student1
				Remaining working hours			11	8,5	4	2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0					Design	In progress	Student2
SPRINT BACKLOG							EFFORT					Code	Finished	Student3
Backlog ID	Task			Type	Status	Responsible					Test	Removed	Student4
	Get a clear vision on all modules and functionality			Design	Finished		2	0,5	0	0					0	0	0
	Technologies exploration			Analysis	Finished		3	2	1	0					0	0	0
BBDD catálogo de productos	Set up Server: SQLAlchemy, dump in DB, vizAPI			Design	Finished		2	2	0	0					0	0	0
	get data.total() to work in server			Code	Finished		0,5	0,5	0	0					0	0	0
	generate JSON and send to browser			Code	Finished		1	1	1	0					0	0	0
	/ncommits should work			Test	Finished		0,5	0,5	0	0					0	0	0
	Adapt SCRUM to this first sprint			Design	Pending		2	2	2	2					0	0	0
									0	0	0
									0	0	0

									0	0

## Graphs
	Project					SPRINT		START		DAYS
	Name of the project					1		25-mar-14		4

Effot Graphic / sub-title / Remaining working hours

Tasks Graphic / sub-title / Remaining Taks

Members Graphic / sub-title / Remaining Working Hours

	25-mar	26-mar	27-mar	28-mar	31-mar	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?	#NOMBRE?
Student1	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Student2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Student3	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Student4	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0